## dashboard
Project Progress Overview
Total Tasks
Completed
In Progress
Avg Progress
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
$46.0K
$9.0K
$15.0K
$22.0K

## pivot_data
Row Labels | Count of Task Name
Completed | 9
In Progress | 15
Not Started | 22
$46.0K
3
Row Labels | Count of Task Name
Consulting | 3
Customer Svc | 3
Development | 3
Engineering | 3
Events | 3
Financial | 3 | $9.0K
Logistics | 3 | $15.0K
Marketing | 4 | $22.0K
Operations | 3
Product Dev | 3
Production | 3
Research | 3
Sales | 3
Support | 3
Training | 3
Row Labels | Average of Progress
Aaron | 1
Alice | 0.78
Bella | 0
Bob | 1
Calvin | 0.4
Charlie | 0.45
Daisy | 0
Diane | 0
Edward | 0
Ethan | 1
Fiona | 0.69
Gabriel | 0
Gary | 0
Hannah | 1
Helen | 0
Ian | 1
Isaac | 0.8
Jane | 0
Julia | 0
Kevin | 0.1
Kyle | 0
Laura | 0.3
Mark | 0.89
Mike | 0
n Nancy | 0
Nathan | 0.5
Olivia | 0
Oscar | 0.5
Patricia | 1
Peter | 0
Quentin | 0
Quinn | 1
Rachel | 0.1
Sam | 0
Tim | 0.3
Tom | 0
Ursula | 0
Victor | 0
Wendy | 0.7
Xavier | 0.78
Yvette | 0
Zoe | 1
Row Labels | Count of Task Name
Jan | 21
Feb | 18
Mar | 7
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project Management Data
Excel Sample Data
Project Management Data
Project Name | Task Name | Assigned to | Start Date | Days Required | Duration Type | End Date | Status | Progress
Marketing | Market Research | Alice | 2024-01-01 | 13 | Short | 2024-01-14 | In Progress | 78%
Marketing | Content Creation | Bob | 2024-01-14 | 14 | Short | 2024-01-28 | Completed | 100%
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | Medium | 2024-02-19 | In Progress | 45%
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | Medium | 2024-03-14 | Not Started | 0%
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | Medium | 2024-01-20 | Completed | 100%
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | Short | 2024-01-30 | In Progress | 78%
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | Medium | 2024-02-29 | Not Started | 0%
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | Medium | 2024-02-23 | Completed | 100%
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | Medium | 2024-03-20 | Completed | 100%
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | Long | 2024-04-20 | Not Started | 0%
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | Medium | 2024-02-24 | In Progress | 10%
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | Medium | 2024-02-09 | In Progress | 78%
Financial | Investment Planning | Mark | 2024-03-19 | 25 | Medium | 2024-04-13 | Completed | 100%
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | Medium | 2024-01-25 | In Progress | 50%
Research | Data Collection | Olivia | 2024-01-26 | 32 | Long | 2024-02-27 | Not Started | 0%
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | Long | 2024-03-26 | Not Started | 0%
Development | Software Development | Quinn | 2024-01-02 | 36 | Long | 2024-02-07 | Completed | 100%
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | Long | 2024-03-13 | Not Started | 0%
Development | Code Review | Sam | 2024-03-14 | 30 | Long | 2024-04-13 | Not Started | 0%
Production | Manufacturing | Tim | 2024-01-03 | 47 | Long | 2024-02-19 | In Progress | 30%
Production | Quality Control | Ursula | 2024-02-17 | 27 | Long | 2024-03-15 | Not Started | 0%
Production | Packaging Design | Victor | 2024-03-14 | 22 | Medium | 2024-04-05 | Not Started | 0%
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | Long | 2024-03-03 | In Progress | 70%
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | Medium | 2024-01-26 | In Progress | 78%
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | Long | 2024-03-09 | Not Started | 0%
Support | Technical Support | Zoe | 2024-01-01 | 25 | Medium | 2024-01-26 | Completed | 100%
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | Long | 2024-02-27 | Completed | 100%
Support | Software Updates | Bella | 2024-03-02 | 22 | Medium | 2024-03-24 | Not Started | 0%
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | Long | 2024-02-02 | In Progress | 40%
Operations | Inventory Management | Diane | 2024-02-03 | 25 | Medium | 2024-02-28 | Not Started | 0%
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | Medium | 2024-03-20 | Not Started | 0%
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | Long | 2024-02-06 | In Progress | 60%
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | Long | 2024-03-05 | Not Started | 0%
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | Medium | 2024-03-31 | Not Started | 0%
Training | Employee Training | Isaac | 2024-01-04 | 27 | Long | 2024-01-31 | In Progress | 80%
Training | Certification Programs | Jane | 2024-01-28 | 30 | Long | 2024-02-27 | Not Started | 0%
Training | Skill Development | Kyle | 2024-02-28 | 22 | Medium | 2024-03-21 | Not Started | 0%
Events | Event Planning | Laura | 2024-01-03 | 25 | Medium | 2024-01-28 | In Progress | 30%
Events | Conference Management | Mike | 2024-02-03 | 20 | Medium | 2024-02-23 | Not Started | 0%
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | Long | 2024-03-30 | Not Started | 0%
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | Medium | 2024-01-28 | In Progress | 50%
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | Long | 2024-02-28 | Completed | 100%
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | Medium | 2024-04-18 | Not Started | 0%
Engineering | Product Design | Rachel | 2024-01-02 | 25 | Medium | 2024-01-27 | In Progress | 20%
Engineering | System Integration | Sam | 2024-02-02 | 22 | Medium | 2024-02-24 | Not Started | 0%
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | Long | 2024-03-21 | Not Started | 0%